## BM-DEV-01-09
[21 empty] | Dev1 |  |  |  | Dev2 |  |  |  | Fixbug |  |  |  | Release
[21 empty] | Test | [7 empty] | Demo |  |  |  | Maintain
Name: | [16 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21
PM: |  | Technical Leader: | [14 empty] | 2015-12-21 | [6 empty] | 2015-12-28 | [6 empty] | 2016-01-04 | [6 empty] | 2016-01-11 | [6 empty] | 2016-01-18 | [6 empty] | 2016-01-25 | [6 empty] | 2016-02-01 | [6 empty] | 2016-02-08 | [6 empty] | 2016-02-15 | [6 empty] | 2016-02-22 | [6 empty] | 2016-02-29 | [6 empty] | 2016-03-07 | [6 empty] | 2016-03-14 | [6 empty] | 2016-03-21 | [6 empty] | 2016-03-28 | [6 empty] | 2016-04-04 | [6 empty] | 2016-04-11 | [6 empty] | 2016-04-18 | [6 empty] | 2016-04-25 | [6 empty] | 2016-05-02 | [6 empty] | 2016-05-09
Created: | [16 empty] | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日
ID | Category | Sub category | Function | Est. Effort (MD) | Est. Start Date | Est. End Date | Act. Effort (MD) | Act. Start Date | Act. End Date | Status | % Complete | Assign to | Progress Status | Risk | Reference | Note | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
C_0010 | Phân tích thiết kế Lần I | Brainstorm lên list chức năng | Ý kiến thành viên > excel | man/day | 19/12/2019 | 19/12/2019 |  |  |  | Inprogress |  | Người chịu trách nhiệm | 0 | rủi ro |  | File excel bao gồm danh sách chức năng có các cột: Nhóm chức năng, tên chức năng, người sử dụng, độ ưu tiên | bar: 2015-12-21 月 21
C_0011 |  | Chốt danh sách màn hình chính sẽ làm | Excel > họp > nhóm > schedule |  | 20/12/2019 | 20/12/2019 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0012 |  | Phân công việc phân tích chi tiết chức năng | Schedule > điền tên |  | 20/12/2019 | 20/12/2019 | [6 empty] | 0 |  |  | Phân mỗi người nhận phân tích một số chức năng -- Đầu vào (các trường) -- Đầu ra (lưu vào db, gửi mail, chuyển màn hình khác, thông báo, …) -- Vẽ wireframe giao diện màn hình -- Danh sách chức năng con | bar: 2015-12-21 月 21
C_0013 |  | Trình bày với nhóm và bảo vệ, thay đổi | Cả nhóm > mỗi chức năng 1 file excel |  | 22/12/2019 | 22/12/2019 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0014 |  | Chốt lần 1 wireframe với khách hàng | excel > ý kiến khách > hoặc câu đã OK |  | 22/12/2019 | 22/12/2019 | [6 empty] | 0 |  |  | Nhận feedback và sửa lại nếu cần | bar: 2015-12-21 月 21
C_0020 | Phân tích thiết kế Lần II | Làm mịn,, mượt bản phân tích của mình | excelv1 > v2 |  | 23/12/2019 | 23/12/2019 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0021 |  | Gửi các bên liên quan review lần cuối | excel > ý kiến khách > hoặc câu đã OK |  | 23/12/2019 | 23/12/2019 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0022 |  | Sửa lại lần cuối | excelv2 > final |  | 24/12/2019 | 24/12/2019 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0030 | màn hình nhập thông tin sinh viên | vẽ wireframe | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0031 |  | thiết kế Database | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 月 21
C_0032 |  | Làm giao diện HTML | git |  | 2020-01-06 | 2020-01-08 | [6 empty] | 0 | bar: 2015-12-21 月 21 to 2015-12-21 火 22
|  | api design | typescript |  | 2020-01-10 | 2020-01-14 | bar: 2015-12-21 月 21 to 2015-12-21 火 22
|  | code frontend | typescript |  | 2020-01-15 | 2020-01-20 | bar: 2015-12-21 月 21 to 2015-12-21 火 22
|  | code backend | typescript |  | 2020-01-15 | 2020-01-20 | bar: 2015-12-21 月 21 to 2015-12-21 火 22
C_0040 | màn hình duyệt | vẽ wireframe | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 月 21 to 2015-12-21 火 22
C_0041 |  | thiết kế Database | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 火 22
C_0042 |  | Làm giao diện HTML | git |  | 2020-01-06 | 2020-01-08 | [6 empty] | 0 | bar: 2015-12-21 火 22
C_0043 |  | api design | typescript |  | 2020-01-10 | 2020-01-14 | [6 empty] | 0 | bar: 2015-12-21 火 22
|  | code frontend | typescript |  | 2020-01-15 | 2020-01-20 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | code backend | typescript |  | 2020-01-15 | 2020-01-20 | [6 empty] | 0 | bar: 2015-12-21 水 23
| màn hình danh sách checkin | vẽ wireframe | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | thiết kế Database | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | Làm giao diện HTML | git |  | 2020-01-06 | 2020-01-08 | bar: 2015-12-21 水 23
|  | api design | typescript |  | 2020-01-10 | 2020-01-14 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | code frontend | typescript |  | 2020-01-15 | 2020-01-20 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | code backend | typescript |  | 2020-01-15 | 2020-01-20 | [6 empty] | 0 | bar: 2015-12-21 水 23
| màn hình danh sách sinh viên | vẽ wireframe | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | thiết kế Database | excel |  | 2020-01-03 | 2020-01-06 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | Làm giao diện HTML | git |  | 2020-01-06 | 2020-01-08 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | api design | typescript |  | 2020-01-10 | 2020-01-14 | [6 empty] | 0 | bar: 2015-12-21 水 23
|  | code frontend | typescript |  | 2020-01-15 | 2020-01-20 | bar: 2015-12-21 水 23
|  | code backend | typescript |  | 2020-01-15 | 2020-01-20 | [6 empty] | 0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23
0 | bar: 2015-12-21 水 23 to 2015-12-21 木 24
0 | bar: 2015-12-21 水 23 to 2015-12-21 木 24
|  |  | Total | 0 | MD |  | 0 | MD
|  |  |  | 0 | MM |  | 0 | MM
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
Week 12 = [Week 11]+7
Week 13 = [Week 12]+7
Week 14 = [Week 13]+7
Week 15 = [Week 14]+7
Week 16 = [Week 15]+7
Week 17 = [Week 16]+7
Week 18 = [Week 17]+7
Week 19 = [Week 18]+7
Week 20 = [Week 19]+7
Week 21 = [Week 20]+7
Progress Status = IF(AND([Act. End Date]<>"",[Act. End Date]>[Est. End Date]),Data!$E3,IF(AND(AND([Est. End Date]<TODAY(),[Est. End Date]<>""),AND([Status]<>Data!$D4,[Status]<>Data!$D5)),Data!$E3,Data!$E2))

## Data
Assignee | Start date | Focus rate | Status | Progress Status | HOLIDAY